## Sheet1
LINE_NUMBER | SHOP_ORDER_IDENTIFIER | PARENT_SOI | SUPERINTENDENT | TEAM | GROUP_PRODUCTION_LOCATION | CURRENT_CONTROL_STATION_IDENT | SCHEDULE_DURATION | FIRST_AVAILABLE_TS | SCHED_START | SCHED_COMP | ACT_START | ACT_COMP | SCHEDULE_METHOD
1261 | FAD29VFJB0370 |  | S-CF-POSITION 0 | P00-CF-AFT EMP | 787 Charleston Final Assembly | 700 | 90 | 2025-06-18 11:49 | 2025-07-10 00:25 | 2025-07-10 01:55 | 2025-07-10 00:53 | 2025-07-10 04:05 | SCHEDULE EDITOR
1246 | FAD29BFJB0104 |  | S-CF-POSITION 1 | P11-CF-FBJFWD | 787 Charleston Final Assembly | 711 | 90 | 2025-03-27 06:10 | 2025-04-10 15:25 | 2025-04-10 16:55 | 2025-04-10 21:30 | 2025-04-11 07:17 | SCHEDULE EDITOR
1245 | FAD2BIMTNF4A5 |  | S-CF-POSITION 2 | P22-CF-ADECK | 787 Charleston Final Assembly | 722 | 58 | 2025-04-02 05:58 | 2025-04-22 16:40 | 2025-04-22 17:38 | 2025-04-22 15:45 | 2025-04-22 20:41 | SCHEDULE EDITOR
1264 | FAD2BILGNC22F |  | S-CF-POSITION 2 | P33-CF-ADECK | 787 Charleston Final Assembly | 733 | 30 | 2025-07-22 11:04 | 2025-08-25 12:40 | 2025-08-25 13:10 | 2025-09-02 12:15 | 2025-09-02 13:47 | SCHEDULE EDITOR
1244 | FADQSWITY222R |  | S-CF-POSITION 1 | STC-CF-SYSTNKCL | 787 Charleston Final Assembly | 733 | 210 | 2025-03-26 04:36 | 2025-04-24 01:42 | 2025-04-24 05:12 | 2025-06-09 16:27 | 2025-06-19 19:07 | SCHEDULE EDITOR
1257 | FAD29ICSNL43A |  | S-CF-POSITION 2 | P23-CF-BDECK | 787 Charleston Final Assembly | 722 | 300 | 2025-06-12 06:17 | 2025-07-01 06:10 | 2025-07-01 11:10 | 2025-07-01 06:06 | 2025-07-01 10:45 | SCHEDULE EDITOR
1277 | FAD29WWTB010L |  | S-CF-POSITION 0 | P00-CF-WING BLD | 787 Charleston Final Assembly | 516 | 30 | 2025-09-02 03:55 | 2025-09-29 06:40 | 2025-09-29 07:10 | 2025-09-29 11:34 | 2025-09-29 11:38 | SCHEDULE EDITOR
1214 | NC6529059_A_001_001 | FADCEILGN0001 | S-CF-FGI | FGI-CF-CUSREADY | 787 Charleston Final Assembly | 744 | 69299 | 2025-04-14 04:05 | 2025-02-04 20:00 | 2025-03-24 23:59 | 2025-05-13 10:27 | 2025-05-21 12:22 | SCHEDULE
1209 | FAD29WBJB172B |  | S-CF-POSITION 1 | P11-CF-WBJ | 787 Charleston Final Assembly | 711 | 59 | 2025-06-23 05:06 | 2025-07-09 01:13 | 2025-07-09 02:12 | 2025-07-09 13:37 | 2025-07-09 14:39 | SCHEDULE EDITOR
1249 | FAD29WTSW042R |  | S-CF-POSITION 0 | P00-CF-WING BLD | 787 Charleston Final Assembly | 700 | 124 | 2025-04-03 08:48 | 2025-04-22 09:08 | 2025-04-22 11:12 | 2025-04-22 06:04 | 2025-04-22 07:39 | SCHEDULE EDITOR
1244 | FAD01BOSEFX02 |  | S-CF-POSITION 0 | P00-CF-FUSE | 787 Charleston Final Assembly | 700 | 30 | 2025-02-17 08:42 | 2025-03-20 00:30 | 2025-03-20 01:00 | 2025-03-20 01:07 | 2025-04-14 05:11 | SCHEDULE EDITOR
1205 | CI6632849_A_001_001_ | FADCEILGN0006 | S-CF-OTHER | INT-CF-VENDOR | 787 Charleston Final Assembly | 535 | 241919 | 2025-08-14 12:52 | 2025-03-12 | 2025-08-26 23:59 | 2025-08-18 09:56 | 2025-08-26 18:39 | SCHEDULE
1251 | NC6572577_A_001_001 | FAD29WFTB835R | S-CF-POSITION 3 | TST-CF-TEAM A | 787 Charleston Final Assembly | 733 | 60 | 2025-06-02 20:47 | 2025-06-04 12:00 | 2025-06-04 13:00 | 2025-06-04 04:34 | 2025-06-04 13:48 | WAVE
1262 | FAD29WFLB621R |  | S-CF-POSITION 3 | WNG-CF-EXT | 787 Charleston Final Assembly | 733 | 139 | 2025-07-10 05:27 | 2025-08-22 17:26 | 2025-08-22 19:45 | 2025-08-22 13:20 | 2025-08-22 19:54 | SCHEDULE EDITOR
1276 | FAD01TES05043 |  | S-CF-POSITION 3 | TST-CF-TEAM B | 787 Charleston Final Assembly | 711 | 70 | 2025-09-04 04:34 | 2025-10-03 17:55 | 2025-10-03 19:05 | 2025-10-03 21:24 | 2025-10-03 22:21 | SCHEDULE EDITOR
1239 | PU6565104_A_001_001 | FAD2B00EDIS1A | S-CF-FGI | FGI-CF-CUSREADY | 787 Charleston Final Assembly | 744 | 2880 | 2025-05-22 09:35 | 2025-04-27 20:00 | 2025-04-29 20:00 | 2025-05-31 08:27 | 2025-06-03 20:39 | SCHEDULE
1209 | FAD2BILGNT05C |  | S-CF-POSITION 1 | P11-CF-FBJFWD | 787 Charleston Final Assembly | 711 | 15 | 2025-06-23 05:11 | 2025-07-14 15:22 | 2025-07-14 15:37 | 2025-07-14 14:41 | 2025-07-14 15:58 | SCHEDULE EDITOR
1243 | CI6523020_A_001_001_ | FADVCINTSR000 | S-CF-OTHER | INT-CF-VENDOR | 787 Charleston Final Assembly | 535 | 103919 | 2025-04-04 12:41 | 2025-03-09 20:00 | 2025-05-20 23:59 | 2025-06-03 11:21 | 2025-06-03 12:53 | SCHEDULE
1247 | FAD2BILGNSRF1 |  | S-CF-POSITION 0 | P00-CF-FUSE | 787 Charleston Final Assembly | 700 | 60 | 2025-03-24 09:03 | 2025-04-10 23:10 | 2025-04-11 00:10 | 2025-04-11 01:20 | 2025-04-11 05:11 | SCHEDULE EDITOR
1254 | FAD2BIMTNM0RF |  | S-CF-POSITION 2 | P22-CF-ADECK | 787 Charleston Final Assembly | 722 | 60 | 2025-05-29 06:46 | 2025-06-20 07:10 | 2025-06-20 08:10 | 2025-06-20 09:34 | 2025-06-20 11:42 | SCHEDULE EDITOR
1266 | FAD2BILGNSD01 |  | S-CF-POSITION 2 | P23-CF-ADECK | 787 Charleston Final Assembly | 722 | 20 | 2025-07-29 06:23 | 2025-08-23 12:00 | 2025-08-23 12:20 | 2025-08-23 12:52 | 2025-08-23 13:31 | SCHEDULE EDITOR
1256 | FAD2BIMTN1C08 |  | S-CF-POSITION 0 | P00-CF-FUSE | 787 Charleston Final Assembly | 700 | 160 | 2025-05-19 08:57 | 2025-06-04 02:50 | 2025-06-04 05:30 | 2025-06-04 02:35 | 2025-06-04 05:44 | SCHEDULE EDITOR
1248 | FAD03ISTN38YM |  | S-CF-POSITION 2 | P23-CF-ADECK | 787 Charleston Final Assembly | 733 | 60 | 2025-04-18 05:13 | 2025-05-07 06:45 | 2025-05-07 07:45 | 2025-05-07 05:49 | 2025-05-09 18:50 | SCHEDULE EDITOR
1240 | PU6516180_A_001_001 | FADCEILGN0007 | S-CF-CUSTREADY | P33-CF-CUSREADY | 787 Charleston Final Assembly | 733 | 31919 | 2025-03-27 19:46 | 2025-03-13 20:00 | 2025-04-04 23:59 | 2025-03-28 10:41 | 2025-03-28 13:56 | SCHEDULE
1269 | CI6653505_A_001_001_ | FAD2BILGNC00A | S-CF-POSITION 2 | P22-CF-ADECK | 787 Charleston Final Assembly | 722 | 30479 | 2025-09-08 09:27 | 2025-09-02 20:00 | 2025-09-23 23:59 | 2025-09-08 11:51 | 2025-09-09 09:13 | SCHEDULE
1271 | FAD29VFRB0094 |  | S-CF-POSITION 0 | P00-CF-VFIN | 787 Charleston Final Assembly | 523 | 150 | 2025-07-14 03:38 | 2025-08-07 08:30 | 2025-08-07 11:00 | 2025-08-08 08:25 | 2025-08-08 10:21 | SCHEDULE EDITOR
1268 | FAD29WTSW324L |  | S-CF-POSITION 1 | LGR-CF-LGRUWF | 787 Charleston Final Assembly | 711 | 90 | 2025-07-29 04:54 | 2025-08-22 12:00 | 2025-08-22 13:30 | 2025-08-22 10:14 | 2025-08-22 11:07 | SCHEDULE EDITOR
1246 | FADCEBFJB0002 |  | S-CF-POSITION 1 | P11-CF-FBJFWD | 787 Charleston Final Assembly | 711 | 60 | 2025-03-27 06:20 | 2025-04-14 06:10 | 2025-04-14 07:10 | 2025-04-15 06:09 | 2025-04-15 21:48 | SCHEDULE EDITOR
1275 | FAD29WTSS100L |  | S-CF-POSITION 0 | P00-CF-WING BLD | 787 Charleston Final Assembly | 700 | 260 | 2025-08-21 18:31 | 2025-09-15 14:45 | 2025-09-15 19:05 | 2025-09-15 15:12 | 2025-09-15 23:02 | SCHEDULE EDITOR
1266 | FAD2BIECWSP96 |  | S-CF-POSITION 0 | P00-CF-FUSE | 787 Charleston Final Assembly | 700 | 14 | 2025-07-11 01:36 | 2025-07-31 06:45 | 2025-07-31 06:59 | 2025-07-31 07:13 | 2025-07-31 09:03 | SCHEDULE EDITOR
1273 | FAD01FDSA0008 |  | S-CF-MHE/TOL | MHE-CF-CAM | 787 Charleston Final Assembly | 722 | 24719 | 2025-08-29 06:31 | 2025-09-23 20:00 | 2025-10-10 23:59 | 2025-09-25 11:19 | 2025-09-25 11:21 | SCHEDULE
1263 | FAD2BIFCNC36F |  | S-CF-POSITION 1 | P11-CF-FBJAFT | 787 Charleston Final Assembly | 711 | 45 | 2025-07-07 05:36 | 2025-07-30 03:30 | 2025-07-30 04:15 | 2025-07-30 22:52 | 2025-07-31 05:38 | SCHEDULE EDITOR
1265 | FAD01WTSC291L |  | S-CF-POSITION 3 | WNG-CF-EXT | 787 Charleston Final Assembly | 722 | 180 | 2025-07-24 06:37 | 2025-08-13 06:17 | 2025-08-13 09:17 | 2025-08-13 09:47 | 2025-08-19 07:44 | SCHEDULE EDITOR
1268 | FAD29WFTB540R |  | S-CF-POSITION 3 | WNG-CF-EXT | 787 Charleston Final Assembly | 722 | 6051 | 2025-08-07 18:46 | 2025-08-29 18:09 | 2025-09-02 23:00 | 2025-09-02 16:58 | 2025-09-13 19:17 | SCHEDULE EDITOR
1243 | FAD29WBJB173L |  | S-CF-POSITION 1 | P11-CF-WBJ | 787 Charleston Final Assembly | 711 | 75 | 2025-03-07 04:37 | 2025-03-20 06:00 | 2025-03-20 07:15 | 2025-03-20 09:10 | 2025-03-20 13:23 | SCHEDULE EDITOR
1264 | NC6506092_D_013_001 | NC6506092_C_012_001 | S-CF-POSITION 1 | P11-CF-FBJAFT | 787 Charleston Final Assembly | 711 | 15 | 2025-04-21 13:45 | 2025-08-01 03:45 | 2025-08-01 04:00 | 2025-08-01 03:42 | 2025-08-04 04:54 | SCHEDULE EDITOR
1266 | CI6646999_A_001_001 | FADCEWWSB005L | S-CF-POSITION 1 | LGR-CF-LGRUWF | 787 Charleston Final Assembly | 565 | 20399 | 2025-08-28 23:09 | 2025-08-19 20:00 | 2025-09-02 23:59 | 2025-09-02 12:36 | 2025-09-02 16:26 | SCHEDULE
1243 | FAD29FOWBC16R |  | S-CF-POSITION 3 | WNG-CF-EXT | 787 Charleston Final Assembly | 733 | 109 | 2025-03-20 04:53 | 2025-04-16 06:08 | 2025-04-16 07:57 | 2025-04-05 12:43 | 2025-04-25 09:21 | SCHEDULE EDITOR
1262 | CI6621040_A_001_001_ | FADVCINTSR000 | S-CF-OTHER | INT-CF-VENDOR | 787 Charleston Final Assembly | 535 | 114059 | 2025-07-31 11:36 | 2025-07-07 19:00 | 2025-09-24 23:59 | 2025-09-30 14:40 | 2025-09-30 16:34 | SCHEDULE
1263 | PU6654269_A_001_001_N/A | FADCEILGN0003 | S-CF-CUSTREADY | P33-CF-CUSREADY | 787 Charleston Final Assembly | 733 | 34799 | 2025-09-08 18:51 | 2025-08-03 20:00 | 2025-08-27 23:59 | 2025-09-09 09:45 | 2025-09-09 11:06 | SCHEDULE
1278 | NC6407755_C_010_001 | FAD20VFJB0130 | S-CF-POSITION 0 | P00-CF-AFT EMP | 787 Charleston Final Assembly | 700 | 15 | 2025-08-29 04:00 | 2025-09-26 05:26 | 2025-09-26 05:41 | 2025-09-26 04:46 | 2025-09-26 06:32 | SCHEDULE EDITOR
1249 | FAD2BISTN08AV |  | S-CF-POSITION 2 | P23-CF-ADECK | 787 Charleston Final Assembly | 722 | 75 | 2025-04-24 05:54 | 2025-05-12 18:25 | 2025-05-12 19:40 | 2025-05-12 19:37 | 2025-05-12 21:37 | SCHEDULE EDITOR
1276 | FAD2BILGNGC3F |  | S-CF-POSITION 1 | P11-CF-FBJFWD | 787 Charleston Final Assembly | 711 | 30 | 2025-09-04 04:58 | 2025-10-03 08:10 | 2025-10-03 08:40 | 2025-10-03 06:19 | 2025-10-03 07:26 | SCHEDULE EDITOR
1265 | PU6644149_A_001_001 | FADCEILGN0003 | S-CF-CUSTREADY | P33-CF-CUSREADY | 787 Charleston Final Assembly | 733 | 21839 | 2025-08-26 11:52 | 2025-08-11 20:00 | 2025-08-26 23:59 | 2025-08-28 09:07 | 2025-09-03 08:30 | SCHEDULE
1270 | FAD29LMSW0622 |  | S-CF-POSITION 2 | P23-CF-BDECK | 787 Charleston Final Assembly | 722 | 90 | 2025-08-18 06:34 | 2025-09-09 07:30 | 2025-09-09 09:00 | 2025-09-09 08:49 | 2025-09-09 19:28 | SCHEDULE EDITOR
1240 | PU6519524_A_001_001 | FADCEILGN0003 | S-CF-CUSTREADY | P33-CF-CUSREADY | 787 Charleston Final Assembly | 733 | 31919 | 2025-04-01 12:23 | 2025-03-13 20:00 | 2025-04-04 23:59 | 2025-04-02 22:34 | 2025-04-02 23:01 | SCHEDULE
1252 | FAD2BILGNP15M |  | S-CF-POSITION 0 | P00-CF-FUSE | 787 Charleston Final Assembly | 700 | 120 | 2025-04-22 08:59 | 2025-05-08 06:10 | 2025-05-08 08:10 | 2025-05-08 06:38 | 2025-05-08 11:00 | SCHEDULE EDITOR
1266 | FAD01925BD13L |  | S-CF-POSITION 2 | P22-CF-DOOR | 787 Charleston Final Assembly | 722 | 30 | 2025-07-29 06:19 | 2025-08-23 13:20 | 2025-08-23 13:50 | 2025-08-23 11:07 | 2025-08-23 12:06 | SCHEDULE EDITOR
1261 | FAD2BEBUP080L |  | S-PL-PROPULSION | 7-PSC-PL-EBU | 787 Charleston Final Assembly | 583 | 0 | 2025-07-02 03:53 | 2025-07-24 17:00 | 2025-07-24 17:00 | 2025-07-30 05:43 | 2025-07-31 08:21 | WAVE
1263 | FAD2BICSNAUXA |  | S-CF-POSITION 2 | P23-CF-BDECK | 787 Charleston Final Assembly | 722 | 15 | 2025-07-15 06:28 | 2025-08-07 09:30 | 2025-08-07 09:45 | 2025-08-07 08:15 | 2025-08-07 09:44 | SCHEDULE EDITOR
1255 | FAD2BTES33004 |  | S-CF-POSITION 3 | TST-CF-TEAM D | 787 Charleston Final Assembly | 733 | 230 | 2025-06-03 04:24 | 2025-07-03 07:40 | 2025-07-03 11:30 | 2025-07-05 07:15 | 2025-09-03 11:55 | SCHEDULE EDITOR
1275 | FAD29WBJB7841 |  | S-CF-POSITION 1 | STC-CF-SEAL | 787 Charleston Final Assembly | 577 | 80 | 2025-09-08 03:56 | 2025-10-06 08:01 | 2025-10-06 09:21 | 2025-10-02 08:30 | 2025-10-02 13:28 | SCHEDULE EDITOR
1250 | PU6574477_A_001_001 | FADVCINTSR000 | S-CF-OTHER | INT-CF-VENDOR | 787 Charleston Final Assembly | 535 | 60779 | 2025-06-04 10:03 | 2025-04-23 19:00 | 2025-06-04 23:59 | 2025-06-09 14:16 | 2025-06-10 09:25 | SCHEDULE
1246 | FAD01HSSW820R |  | S-CF-POSITION 1 | P11-CF-EMPFUSE | 787 Charleston Final Assembly | 711 | 45 | 2025-03-27 06:04 | 2025-04-14 10:45 | 2025-04-14 11:30 | 2025-04-14 12:34 | 2025-04-14 17:10 | SCHEDULE EDITOR
1262 | FAD29WBJB7654 |  | S-CF-POSITION 1 | STC-CF-SEAL | 787 Charleston Final Assembly | 577 | 4310 | 2025-07-08 04:07 | 2025-08-01 15:40 | 2025-08-04 15:30 | 2025-08-01 20:46 | 2025-08-04 17:11 | SCHEDULE EDITOR
1183 | PU6226749_A_001_001 | FAD2BTES44062 | S-CF-FGI | FGI-CF-TEST | 787 Charleston Final Assembly | 744 | 437939 | 2024-03-29 12:17 | 2024-01-11 20:00 | 2024-11-10 22:59 | 2025-07-20 11:48 | 2025-07-23 21:03 | WAVE
1269 | FAD01WMLB142R |  | S-CF-POSITION 0 | P00-CF-WING BLD | 787 Charleston Final Assembly | 700 | 75 | 2025-07-24 08:18 | 2025-08-21 15:41 | 2025-08-21 16:56 | 2025-08-22 22:12 | 2025-08-22 22:31 | SCHEDULE EDITOR
1263 | FADCEILGN0001 |  | S-CF-FGI | FGI-CF-CUSREADY | 787 Charleston Final Assembly | 744 | 10770 | 2025-07-15 04:26 | 2025-08-12 06:10 | 2025-08-19 17:40 | 2025-08-17 05:05 |  | SCHEDULE EDITOR
1251 | FAD2BILGN4811 |  | S-CF-POSITION 0 | P00-CF-FUSE | 787 Charleston Final Assembly | 700 | 30 | 2025-04-16 08:58 | 2025-05-01 09:10 | 2025-05-01 09:40 | 2025-05-01 12:41 | 2025-05-01 13:29 | SCHEDULE EDITOR
1205 | FAD29ICSN04FR |  | S-CF-POSITION 2 | P23-CF-BDECK | 787 Charleston Final Assembly | 722 | 235 | 2024-05-06 05:07 | 2025-06-12 16:40 | 2025-06-12 20:35 | 2025-06-17 17:15 | 2025-06-17 23:47 | SCHEDULE EDITOR
1270 | FAD01SWLL4900 |  | S-CF-POSITION 3 | TST-CF-TEAM B | 787 Charleston Final Assembly | 722 | 5 | 2025-08-18 06:32 | 2025-09-08 09:35 | 2025-09-08 09:40 | 2025-09-08 05:07 | 2025-09-08 12:35 | SCHEDULE EDITOR
1263 | FAD29WMLB126R |  | S-CF-POSITION 0 | P00-CF-WING BLD | 787 Charleston Final Assembly | 700 | 65 | 2025-06-26 08:20 | 2025-07-16 16:11 | 2025-07-16 17:16 | 2025-07-26 07:48 | 2025-08-11 14:07 | SCHEDULE EDITOR
1267 | FAD29BAJB0171 |  | S-CF-POSITION 1 | P11-CF-FBJAFT | 787 Charleston Final Assembly | 711 | 120 | 2025-07-24 05:03 | 2025-08-15 14:40 | 2025-08-15 16:40 | 2025-08-15 10:46 | 2025-08-27 10:40 | SCHEDULE EDITOR
1248 | FAD01TES78001 |  | S-CF-POSITION 3 | TST-CF-TEAM A | 787 Charleston Final Assembly | 733 | 90 | 2025-04-18 05:11 | 2025-05-22 14:50 | 2025-05-22 16:20 | 2025-05-21 17:20 | 2025-05-21 19:38 | SCHEDULE EDITOR
1253 | FAD2BSWLL3450 |  | S-CF-POSITION 3 | TST-CF-TEAM B | 787 Charleston Final Assembly | 722 | 5 | 2025-05-19 06:09 | 2025-06-04 12:45 | 2025-06-04 12:50 | 2025-06-04 05:47 | 2025-06-05 18:37 | SCHEDULE EDITOR
1270 | FAD2BIMTN2C1A |  | S-CF-POSITION 2 | P22-CF-ADECK | 787 Charleston Final Assembly | 722 | 60 | 2025-08-18 06:38 | 2025-09-12 16:00 | 2025-09-12 17:00 | 2025-09-12 13:38 | 2025-09-12 16:56 | SCHEDULE EDITOR
1243 | PU6503137_A_001_001 | SRR6493715_A_001_001_CN | S-CF-OTHER | INT-CF-VENDOR | 787 Charleston Final Assembly | 535 | 63599 | 2025-03-14 08:05 | 2025-03-09 20:00 | 2025-04-22 23:59 | 2025-04-09 12:57 | 2025-04-09 13:48 | SCHEDULE
1262 | FAD2BILGDL404 |  | S-CF-POSITION 2 | P22-CF-DOOR | 787 Charleston Final Assembly | 722 | 90 | 2025-07-10 06:46 | 2025-08-01 19:16 | 2025-08-01 20:46 | 2025-08-25 07:06 |  | WAVE
1267 | FAD29WFTB231L |  | S-CF-POSITION 0 | P00-CF-WING BLD | 787 Charleston Final Assembly | 700 | 46 | 2025-07-15 08:34 | 2025-08-04 07:35 | 2025-08-04 08:21 | 2025-08-04 04:27 | 2025-08-04 05:27 | SCHEDULE EDITOR
1250 | FAD01TES27006 |  | S-CF-POSITION 3 | TST-CF-TEAM A | 787 Charleston Final Assembly | 733 | 90 | 2025-04-30 04:39 | 2025-05-23 07:42 | 2025-05-23 09:12 | 2025-05-31 12:09 | 2025-05-31 15:02 | SCHEDULE EDITOR
1265 | FAD03ISTN8FDB |  | S-CF-POSITION 2 | P23-CF-ADECK | 787 Charleston Final Assembly | 556 | 50 | 2025-07-25 10:06 | 2025-08-15 20:10 | 2025-08-15 21:00 | 2025-09-29 12:09 | 2025-09-29 13:22 | SCHEDULE EDITOR
1255 | FAD01HSSH264B |  | S-CF-POSITION 1 | P11-CF-EMPFUSE | 787 Charleston Final Assembly | 711 | 70 | 2025-05-23 04:31 | 2025-06-12 10:40 | 2025-06-12 11:50 | 2025-06-12 11:13 | 2025-06-12 12:02 | SCHEDULE EDITOR
1251 | FAD2BIECWS614 |  | S-CF-POSITION 2 | P22-CF-ADECK | 787 Charleston Final Assembly | 722 | 90 | 2025-05-06 05:57 | 2025-05-27 17:40 | 2025-05-27 19:10 | 2025-05-27 20:17 | 2025-05-27 22:20 | SCHEDULE EDITOR
1250 | FAD03ISTN0DEG |  | S-CF-POSITION 2 | P23-CF-ADECK | 787 Charleston Final Assembly | 556 | 22 | 2025-04-30 04:10 | 2025-05-19 07:31 | 2025-05-19 07:53 | 2025-05-19 21:31 | 2025-05-19 23:12 | SCHEDULE EDITOR
1268 | CI6660767_A_001_001_ | FADCEILGN0007 | S-CF-OTHER | INT-CF-VENDOR | 787 Charleston Final Assembly | 535 | 75179 | 2025-09-15 15:06 | 2025-08-03 19:00 | 2025-09-24 23:59 | 2025-09-25 15:16 | 2025-09-25 16:55 | SCHEDULE
1250 | FAD01TES26006 |  | S-CF-POSITION 3 | TST-CF-TEAM C | 787 Charleston Final Assembly | 744 | 100 | 2025-04-30 04:38 | 2025-06-03 01:10 | 2025-06-03 02:50 | 2025-05-31 03:54 | 2025-06-06 03:48 | SCHEDULE EDITOR
1255 | FAD01TES47001 |  | S-CF-POSITION 1 | STC-CF-SYSTNKCL | 787 Charleston Final Assembly | 733 | 165 | 2025-06-03 04:25 | 2025-07-01 00:35 | 2025-07-01 03:20 | 2025-08-13 22:59 | 2025-08-14 04:42 | SCHEDULE EDITOR
1266 | FAD2BIMTNE2RF |  | S-CF-POSITION 2 | P22-CF-ADECK | 787 Charleston Final Assembly | 722 | 60 | 2025-07-29 06:16 | 2025-08-28 07:00 | 2025-08-28 08:00 | 2025-08-28 11:44 | 2025-08-28 12:50 | SCHEDULE EDITOR
1272 | FAD29WWTB440L |  | S-CF-POSITION 0 | P00-CF-WING BLD | 787 Charleston Final Assembly | 516 | 60 | 2025-08-05 03:54 | 2025-09-02 11:15 | 2025-09-02 12:15 | 2025-09-07 05:57 | 2025-09-07 16:28 | SCHEDULE EDITOR
1258 | FAD03ISTNVGEB |  | S-CF-POSITION 2 | P23-CF-ADECK | 787 Charleston Final Assembly | 556 | 90 | 2025-06-17 03:55 | 2025-07-09 11:15 | 2025-07-09 12:45 | 2025-07-22 10:40 | 2025-07-30 19:26 | SCHEDULE EDITOR
1259 | FADCEICSX999A |  | S-CF-POSITION 2 | P23-CF-BDECK | 787 Charleston Final Assembly | 733 | 1865 | 2025-06-23 04:52 | 2025-07-22 06:35 | 2025-07-23 13:40 | 2025-09-03 14:50 |  | WAVE
1246 | FAD2BIECWH723 |  | S-CF-POSITION 2 | P22-CF-ADECK | 787 Charleston Final Assembly | 722 | 15 | 2025-04-07 05:36 | 2025-04-22 07:10 | 2025-04-22 07:25 | 2025-04-22 07:45 | 2025-04-22 10:53 | SCHEDULE EDITOR
1262 | FAD01925BD02R |  | S-CF-POSITION 2 | P22-CF-DOOR | 787 Charleston Final Assembly | 722 | 430 | 2025-07-14 09:19 | 2025-07-30 06:10 | 2025-07-30 13:20 | 2025-07-30 10:53 | 2025-07-31 15:39 | SCHEDULE EDITOR
1264 | FAD01WLSW823L |  | S-CF-POSITION 0 | P00-CF-WING BLD | 787 Charleston Final Assembly | 700 | 72 | 2025-07-09 11:36 | 2025-07-23 06:10 | 2025-07-23 07:22 | 2025-07-25 05:09 | 2025-07-25 08:32 | SCHEDULE EDITOR
1263 | FAD29FOWBC91L |  | S-CF-POSITION 1 | P11-CF-WBJ | 787 Charleston Final Assembly | 700 | 4770 | 2025-06-26 07:54 | 2025-07-18 06:40 | 2025-07-21 14:10 | 2025-07-18 10:15 | 2025-07-18 13:16 | SCHEDULE EDITOR
1260 | FAD29WFTB462L |  | S-CF-POSITION 0 | P00-CF-WING BLD | 787 Charleston Final Assembly | 700 | 125 | 2025-06-09 08:41 | 2025-06-30 06:10 | 2025-06-30 08:15 | 2025-07-01 11:15 | 2025-07-01 13:08 | SCHEDULE EDITOR
1250 | FAD29EPWP712L |  | S-CF-POSITION 0 | P00-CF-WING BLD | 787 Charleston Final Assembly | 700 | 55 | 2025-04-10 08:45 | 2025-04-25 17:25 | 2025-04-25 18:20 | 2025-04-25 22:54 | 2025-04-26 01:25 | SCHEDULE EDITOR
1248 | FAD29WTCB100R |  | S-CF-POSITION 1 | P11-CF-WBJ | 787 Charleston Final Assembly | 700 | 30 | 2025-03-28 08:37 | 2025-04-21 08:25 | 2025-04-21 08:55 | 2025-04-21 06:01 | 2025-04-21 07:34 | SCHEDULE EDITOR
1246 | FAD2BILGNPH2M |  | S-CF-POSITION 0 | P00-CF-FUSE | 787 Charleston Final Assembly | 700 | 70 | 2025-03-20 08:57 | 2025-04-03 06:10 | 2025-04-03 07:20 | 2025-04-03 07:02 | 2025-04-03 10:54 | SCHEDULE EDITOR
1209 | FAD2BIMTNF3TC |  | S-CF-POSITION 2 | P33-CF-ADECK | 787 Charleston Final Assembly | 733 | 90 | 2025-07-01 05:30 | 2025-07-31 17:40 | 2025-07-31 19:10 | 2025-08-09 13:53 | 2025-08-09 17:55 | SCHEDULE EDITOR
1253 | FAD2BIECW1512 |  | S-CF-POSITION 0 | P00-CF-FUSE | 787 Charleston Final Assembly | 700 | 45 | 2025-04-28 08:55 | 2025-05-19 16:45 | 2025-05-19 17:30 | 2025-05-19 21:16 | 2025-05-22 03:31 | SCHEDULE EDITOR
1260 | FAD2BILGNPH5M |  | S-CF-POSITION 0 | P00-CF-FUSE | 787 Charleston Final Assembly | 700 | 70 | 2025-06-09 08:52 | 2025-06-25 07:20 | 2025-06-25 08:30 | 2025-06-28 14:35 | 2025-06-28 16:26 | SCHEDULE EDITOR
1250 | PU6625767_A_001_001 | FAD2BIMTNF1A1 | S-CF-POSITION 2 | P22-CF-ADECK | 787 Charleston Final Assembly | 722 | 59279 | 2025-08-06 10:27 | 2025-05-14 20:00 | 2025-06-24 23:59 | 2025-08-06 10:47 | 2025-08-19 07:24 | SCHEDULE
1265 | FAD2BISTNP0BR |  | S-CF-POSITION 2 | P23-CF-ADECK | 787 Charleston Final Assembly | 733 | 30 | 2025-07-24 04:56 | 2025-08-15 06:10 | 2025-08-15 06:40 | 2025-08-15 09:52 | 2025-08-15 10:04 | SCHEDULE EDITOR
1255 | FAD29BFJB1031 |  | S-CF-POSITION 1 | P11-CF-FBJFWD | 787 Charleston Final Assembly | 711 | 160 | 2025-05-23 04:39 | 2025-06-10 23:10 | 2025-06-11 01:50 | 2025-06-11 14:50 | 2025-06-11 19:33 | SCHEDULE EDITOR
1272 | FAD20WBJB423R |  | S-CF-POSITION 1 | P11-CF-WBJ | 787 Charleston Final Assembly | 711 | 202 | 2025-08-18 05:13 | 2025-09-09 14:30 | 2025-09-09 17:52 | 2025-09-09 16:36 | 2025-09-09 22:04 | SCHEDULE EDITOR
1245 | FAD29WBJB350L |  | S-CF-POSITION 1 | P11-CF-WBJ | 787 Charleston Final Assembly | 711 | 105 | 2025-03-24 04:38 | 2025-04-08 08:00 | 2025-04-08 09:45 | 2025-04-09 05:04 | 2025-04-09 08:41 | SCHEDULE EDITOR
1252 | FAD29WFLQ1663 |  | S-CF-POSITION 0 | P00-CF-WING BLD | 787 Charleston Final Assembly | 700 | 15 | 2025-04-22 08:46 | 2025-05-09 19:50 | 2025-05-09 20:05 | 2025-05-09 22:33 | 2025-05-10 00:27 | SCHEDULE EDITOR
1259 | FAD01WLAB205R |  | S-CF-MHE/TOL | MHE-CF-TOL0 | 787 Charleston Final Assembly | 711 | 120 | 2025-06-12 04:35 | 2025-06-27 01:00 | 2025-06-27 03:00 | 2025-06-27 06:31 | 2025-06-27 06:32 | WAVE
1264 | CI6645446_A_001_001_ | FAD29EFTB2000 | S-CF-POSITION 2 | P23-CF-BDECK | 787 Charleston Final Assembly | 733 | 27599 | 2025-08-27 12:44 | 2025-08-14 20:00 | 2025-09-02 23:59 | 2025-09-22 14:49 | 2025-09-22 19:28 | SCHEDULE