## Sheet1
RelatedJobNum_Predecessor | JobNum_Successor | MODELNAME | JOBRELTYPENAME | ISHARDRELATIONSHIP | NOTE | LASTMODIFIEDDATE
FAD03BOSS2207 | FAD03BOSS2219 | 10 | FINISH <= START | N | Justification: P, Module on dripshield/support assy (R Gelzer), 2/22/2025, 3504081.; Notes: 2207->2219 true 100% of the time over 2 lines. Slack: 0 | 2025-09-24 20:55
FAD2AWMLB105L | FAD2AWMLB115L | 9 | FINISH <= START | N | Justification: 3575876, Adjust the slat skirts before installing them.; Notes: 105L->115L true 83% of the time over 12 lines. Slack: 0 | 2025-09-24 18:28
FAD01MHFB041X | FAD01TES24009 | 9 | FINISH <= START | N | Justification: SEC 41 reconfigured before testing. NEEDS BEMS NEEDS BEMS; Notes: 041X->4009 true 91% of the time over 160 lines. Slack: 1 | 2025-09-24 17:53
FAD2BISTNBSFL | FAD03ISTN3AAG | 10 | FINISH <= START | N | Justification: P, bulbseal is easier to install prior to loading seats, 7/5/24, 3563331.; Notes: BSFL->3AAG true 100% of the time over 7 lines. Slack: 3 | 2025-09-24 20:29
FAD2BIMTN1L0A | FAD2BIMTN1L04 | 10 | FINISH <= START | N | Justification: P, Attach CRN to AP and coil before galley install (R Gelzer), 9/18/2024, 3504081.; Notes: 1L0A->1L04 true 52% of the time over 19 lines. Slack: 0 | 2025-09-24 20:59
FAD29WMTB270L | FAD29WMTB900L | 8 | FINISH <= START | N | Justification: P, Paint before hanging canoes 3575876; Notes: 270L->900L true 95% of the time over 146 lines. Slack: 0 | 2025-09-24 19:25
FADCEBAJB0005 | FAD29BASV0021 | 8 | FINISH <= START | N | Justification: P, Blanket after customer inspection, 6/13/24, 3531130; Notes: FADCEBAJB0005 -> FAD29BASV0021 relationship true: 84% of the time over 31 instances | 2025-03-14 04:37
FAD29WTSWM810 | FAD29WTSW838R | 8 | FINISH <= START | N | Justification: ; Notes: M810->838R true 97% of the time over 148 lines. Slack: 0 | 2025-09-24 19:39
FAD2BILGNPJ7M | FAD2BBOSPAOL5 | 10 | FINISH <= START | N | Justification: P, Wires route behind ducts (C Martinelli), 5/30/2024, 3504081.; Notes: PJ7M->AOL5 true 0% of the time over 0 lines. Slack: NA | 2025-09-24 20:44
FAD20BFJB1431 | FAD20BFJB1353 | 8 | FINISH <= START | Y | Justification: p, finish drilling before fillet seal, 5/12/25, 3531130.; Notes: 1431->1353 true 100% of the time over 13 lines. Slack: 0 | 2025-09-24 19:30
FAD29WLAB017R | FAD29WBJB241B | 9 | FINISH <= START | N | Justification: P, wings must be aligned prior to work, 2/11/25, 3576348.; Notes: 017R->241B true 75% of the time over 96 lines. Slack: 0 | 2025-09-24 18:23
FAD29BFSWJM32 | FAD20ICSNL53F | 9 | FINISH <= START | N | Justification: P, complete all wiring installations prior to installing ceiling panels,link made using python logic,11-27-2024, 3563331.; Notes: JM32->L53F true 100% of the time over 52 lines. Slack: | 2025-09-24 18:09
FAD01MHMB043X | FAD20WBJB401Z | 8 | FINISH <= START | N | Justification: E, Load 46/43 sections in P0 before starting to avoid overproduction, 1/31/24, 3576348.; Notes: 043X->401Z true 98% of the time over 52 lines. Slack: 5 | 2025-09-24 19:28
FAD01TLABM043 | FAD01901NRSLF | 9 | FINISH <= START | N | Justification: P, remove P0 temp lights downline (R Gelzer), 11/7/24, 3504081.; Notes: M043->RSLF true 100% of the time over 160 lines. Slack: 20 | 2025-09-24 18:38
FAD2BIFCNC00M | FAD03ISTNHODG | 9 | FINISH <= START | N | Justification: P, install carpet prior to loading seats, 5/23/24, 3563331.; Notes: C00M->HODG true 0% of the time over 0 lines. Slack: NA | 2025-09-24 17:58
FAD29BFLB0083 | FAD29BFJB0220 | 10 | FINISH <= START | N | Justification: Q, mark scan holes for drills, 5/29/24, 3531130.; Notes: 0083->0220 true 98% of the time over 96 lines. Slack: 0 | 2025-09-24 20:17
FAD2BENCP500L | FAD2BENCP501L | 8 | FINISH <= START | N | Justification: E, part 1 of TR preps should be completed before part 2E, part 1 of TR preps should be completed before part 2, 3/31/25, 3155355; Notes: 500L->501L true 28% of the time over 28 lines. S | 2025-09-24 19:08
FAD29WBJB7628 | FAD29WBJB7630 | 10 | FINISH <= START | Y | Justification: P, Seal SOW precedence, 9/10/25, 3456276; Notes: 7628->7630 true 69% of the time over 148 lines. Slack: 0 | 2025-09-24 20:49
FAD2BILGNWR3F | FAD03ISTNMMEG | 8 | FINISH <= START | N | Justification: P, install EDWs before loading seats, 08-20-2025, 3563331; Notes: WR3F->MMEG true 100% of the time over 6 lines. Slack: 5 | 2025-09-24 19:26
FAD03ISTNHDBG | FAD03ISTNHDBB | 9 | FINISH <= START | N | Justification: P, must load seats prior to install, 5/2/24, 3563331P, must load seat prior to install, 5/3/24, 3563331.; Notes: HDBG->HDBB true 0% of the time over 0 lines. Slack: NA | 2025-09-24 18:48
FAD29ILGNWR1F | FAD03ISTN4AEG | 8 | FINISH <= START | N | Justification: P, install EDWs before loading seats, 10-23-2024, 35563331.; Notes: WR1F->4AEG true 0% of the time over 0 lines. Slack: NA | 2025-09-24 19:28
FAD2AWTCB505B | FAD2AWTCB509B | 8 | FINISH <= START | N | Justification: E, Maintenance doors should be installed post in tank work for access efficiency, 6/12/24, 3456276.; Notes: 505B->509B true 58% of the time over 12 lines. Slack: 0 | 2025-09-24 19:56
FAD2BIMTN4C81 | FAD2BIMTN4C53 | 10 | FINISH <= START | N | Justification: P, Duct installs on galley off AP (D Mansfield), 8/10/2024, 3504081.; Notes: 4C81->4C53 true 20% of the time over 160 lines. Slack: 0 | 2025-09-26 16:48
FAD2BENCP632R | FAD2BENCP530R | 8 | FINISH <= START | N | Justification: E, it is better to have fully installed the TR hoses before rigging, 3/31/25, 3155355; Notes: 632R->530R true 85% of the time over 28 lines. Slack: 1 | 2025-09-24 19:09
FAD29WBJB437L | FAD29WBJB7809--1 | 8 | FINISH <= START | N | Justification: LINK ADDED BASED ON PRIMARY JOB PRECEDENCE 5/30/25. NEEDS BEMS NEEDS BEMS; Notes: 437L->9--1 true 0% of the time over 0 lines. Slack: NA | 2025-09-24 19:06
FAD2BISTN61YA | FAD03IESPHL06 | 10 | FINISH <= START | N | Justification: Q, install photolums once seats are loaded to prevent damage, 7/5/24, 3563331.; Notes: 61YA->HL06 true 0% of the time over 0 lines. Slack: NA | 2025-09-24 20:14
FADCEBFJB0006 | FAD29ICSN41RF | 10 | FINISH <= START | N | Justification: P, Install firebarrier after inspection, 6/20/24, 3531130.; Notes: 0006->41RF true 60% of the time over 96 lines. Slack: 0 | 2025-09-24 20:34
FAD01BAJB0039 | FAD20BAJB0215 | 8 | FINISH <= START | N | Justification: P, set up drills before drill strap pilots, 5/8/24, 3531130.; Notes: 0039->0215 true 88% of the time over 52 lines. Slack: 0 | 2025-09-24 19:47
FAD20BFJB0210 | FAD2BBFSWP220 | 10 | FINISH <= START | N | Justification: P, FBJ joins stay out doc allows alignemnt after Angles are Clecoed, 8/27/24, 3531130; Notes: FAD20BFJB0210 -> FAD2BBFSWP220 relationship true: 0% of the time over 0 instances | 2025-03-14 05:11
FAD2AICSNL36A | FAD2AICSNL82A | 9 | FINISH <= START | N | Justification: p, vertical sidewall installed before tape, 6/24/24, 3582167.; Notes: L36A->L82A true 83% of the time over 12 lines. Slack: 1 | 2025-09-24 17:50
FAD03IMTN2R54 | FAD2BIMTNF07A | 8 | FINISH <= START | N | Justification: P, install attendant stowage after installing lav to allow access for kickstrips, 7/31/24, 3563331.; Notes: 2R54->F07A true 0% of the time over 0 lines. Slack: NA | 2025-09-24 19:18
FAD03ISTN2EBG | FAD03ISTN2EBB | 8 | FINISH <= START | N | Justification: P, Load passenger seat prior to install, 5/20/24, 3563331.; Notes: 2EBG->2EBB true 100% of the time over 13 lines. Slack: 4 | 2025-09-24 19:59
FAD2AWBJB733L | FAD2AWITF370L | 10 | FINISH <= START | N | Justification: Q, Fillet seal needs to be completed prior to drain valve, 9/7/24, 3456276.; Notes: 733L->370L true 100% of the time over 12 lines. Slack: 3 | 2025-09-24 20:14
FAD29WITF150L | FAD29WITF160L | 9 | FINISH <= START | Y | Justification: E, Sequence of work for BC, 8/7/25, 3456276; Notes: 150L->160L true 66% of the time over 96 lines. Slack: 0 | 2025-09-24 18:23
FAD29WMTB610R | FAD29WMTB630R | 10 | FINISH <= START | N | Justification: P, Need Support installed to be able to align, 6/7/24,2155637.; Notes: 610R->630R true 91% of the time over 148 lines. Slack: 2 | 2025-09-24 20:45
FAD01HSIB0233 | FAD01HSSW816R | 8 | FINISH <= START | N | Justification: P, Brackets have to be installed first, 6/3/24, 3487724.; Notes: 0233->816R true 95% of the time over 160 lines. Slack: 0 | 2025-09-24 19:49
FAD03IMTNML0M | FAD03IMTNF09M | 10 | FINISH <= START | N | Justification: P, BFE monument must be loaded onto the airplane prior to moving it, 6/19/24, 3563331.; Notes: ML0M->F09M true 0% of the time over 0 lines. Slack: NA | 2025-09-24 20:31
FAD2BISTN05TF | FAD03ISTN0IAG | 10 | FINISH <= START | N | Justification: P, install smoke tape before loading seats, 8/21/24, 3563331.; Notes: 05TF->0IAG true 100% of the time over 7 lines. Slack: 6 | 2025-09-24 20:29
FAD03ISTN4BEG | FAD03ISTN4BEB | 9 | FINISH <= START | N | Justification: P, load seats prior to install, 5/14/24, 3563331.; Notes: 4BEG->4BEB true 100% of the time over 7 lines. Slack: 3 | 2025-09-24 18:18
FAD2AWTCB601R | FAD2AWTCB601W | 8 | FINISH <= START | N | Justification: Q, Aqueous wash needs to be complete prior to tool removal to prevent quality defects, 7/25/24, 3456276.; Notes: 601R->601W true 83% of the time over 12 lines. Slack: 0 | 2025-09-24 19:13
FAD01TLANCSP2 | FAD2BISTNC41B--1 | 10 | FINISH <= START | Y | Justification: ; Notes: CSP2->B--1 true 0% of the time over 0 lines. Slack: NA | 2025-09-24 20:06
FAD03ISTNJAAF | FAD03ISTNJAEG | 10 | FINISH <= START | N | Justification: P, prepare passenger seats prior to loading them on the plane, 5/29/24, 3563331.; Notes: JAAF->JAEG true 50% of the time over 2 lines. Slack: -24 | 2025-09-24 20:32
FAD03ISTN3ADG | FAD03ISTN3ADB | 10 | FINISH <= START | N | Justification: P, load passenger seat prior to install, 5/20/24, 3563331.; Notes: 3ADG->3ADB true 100% of the time over 7 lines. Slack: 2 | 2025-09-24 20:29
FAD01HSIB0126 | FAD01HSIB0170 | 9 | FINISH <= START | Y | Justification: P, torque before aeroseal, 9/5/25, 3563331; Notes: 0126->0170 true 86% of the time over 160 lines. Slack: 0 | 2025-09-24 18:31
FAD01MHMB025M | FAD29BOSA268L | 9 | FINISH <= START | N | Justification: P, Install Antennas after AP access is established (R Gelzer), 8/22/2024, 3504081.; Notes: 025M->268L true 100% of the time over 78 lines. Slack: 2 | 2025-09-24 18:27
FAD03IMTNM09M | FAD03ISTNMAAG | 10 | FINISH <= START | N | Justification: P, install BFE monument before loading BC seats, 8/17/24, 356331. NEEDS BEMS NEEDS BEMS; Notes: M09M->MAAG true 6% of the time over 15 lines. Slack: -13 | 2025-09-24 20:14
FAD2AICSN0043 | FAD2AICSN1FLF | 10 | CONCURRENT | N | Justification: Q, install product protection after floor panel install, 6/11/24, 3582167.; Notes: 0043->1FLF true 100% of the time over 12 lines. Slack: 10 | 2025-09-24 20:27
FAD01VFSW8212 | FAD29VFJB0542 | 10 | FINISH <= START | N | Justification: P, Preference, 6/12/24, 3487724.; Notes: 8212->0542 true 32% of the time over 148 lines. Slack: -2 | 2025-09-24 20:50
FAD29WLAB017R | FAD29WFTB4027 | 8 | FINISH <= START | N | Justification: P, align to install markers wing to body, 09/12/2024, 3543740.; Notes: 017R->4027 true 87% of the time over 96 lines. Slack: 0 | 2025-09-24 19:07
FAD2AICSN0043 | FAD2AICSN3FRF | 10 | CONCURRENT | N | Justification: Q, install product protection after floor panel install, 6/11/24, 3582167.; Notes: 0043->3FRF true 100% of the time over 12 lines. Slack: 11 | 2025-09-24 20:31
FADCEBAJB0006 | FAD2AILGNS03A | 10 | FINISH <= START | N | Justification: P, Blanket after customer inspection, 6/24/24, 3531130.; Notes: 0006->S03A true 66% of the time over 12 lines. Slack: 0 | 2025-09-24 20:19
FAD01HLAB0230 | FAD01HSIB0281 | 9 | FINISH <= START | N | Justification: P, part of aft emp critical path, David to provide more detail later, 3/29/2025, 3563331.; Notes: 0230->0281 true 62% of the time over 160 lines. Slack: 0 | 2025-09-24 18:00
FAD03ISTN3BEG | FAD03ISTN3BEB | 10 | FINISH <= START | N | Justification: P, load passenger seat prior to install, 5/14/24, 3563331.; Notes: 3BEG->3BEB true 100% of the time over 7 lines. Slack: 2 | 2025-09-24 20:43
FAD01MHMB025A | FAD2BIMTMW729 | 9 | FINISH <= START | N | Justification: P, Install Window Plugs after AP access is established (R Gelzer), 8/22/2024, 3504081; Notes: FAD01MHMB025A -> FAD2BIMTMW729 relationship true: 100% of the time over 3 instances | 2025-03-22 03:54
FADCEBAJB0001 | FAD29BAJB0245 | 9 | FINISH <= START | N | Justification: P, runs along Str 8L & 8R and may block customer, 2/7/25, 3531130.; Notes: 0001->0245 true 30% of the time over 96 lines. Slack: 0 | 2025-09-24 17:54
FAD2BISTNBSFL | FAD03ISTN6HAG | 8 | FINISH <= START | N | Justification: P, install bulbseal before loading seats, 08-20-2025, 3563331; Notes: BSFL->6HAG true 0% of the time over 0 lines. Slack: NA | 2025-09-24 19:55
FAD03ISTNHFBG | FAD03ISTNHFBB | 8 | FINISH <= START | N | Justification: P, must load seats prior to install, 5/2/24, 3563331P, must load seat prior to install, 5/3/24, 3563331.; Notes: HFBG->HFBB true 0% of the time over 0 lines. Slack: NA | 2025-09-24 19:52
FAD2BSWLLMSDP | FAD01SWLL024A | 10 | FINISH <= START | N | Justification: P, prep equipment before software loads, 3278686, 6/5/25.; Notes: MSDP->024A true 100% of the time over 79 lines. Slack: 3 | 2025-09-24 20:29
FAD29MGSG007L | FAD29FUWBC04L | 9 | FINISH <= START | N | Justification: P, frame assembly to attach panel, 09/10/2024, 3543740.; Notes: 007L->C04L true 87% of the time over 96 lines. Slack: 2 | 2025-09-24 18:22
FAD2BICSNWPT3 | FAD2AICSNW0A1 | 8 | FINISH <= START | N | Justification: P, Heater attaches to trunk run, reference only, work transfer item (R Gelzer), 9/18/2024, 3504081.; Notes: WPT3->W0A1 true 100% of the time over 11 lines. Slack: 3 | 2025-09-24 19:29
FAD20WBJB173R | FAD20WBJB176R | 10 | FINISH <= START | N | Justification: P, 1st torque needs to be applied prior to 2nd torque, 5/29/24,2155637.; Notes: 173R->176R true 84% of the time over 52 lines. Slack: 0 | 2025-09-24 20:32
FAD20BFJB1131 | FAD20BFJB1365 | 8 | FINISH <= START | Y | Justification: P, ME build plan update work H chanel after drilling is complete, 5/12/25, 3531130.; Notes: 1131->1365 true 88% of the time over 52 lines. Slack: 0 | 2025-09-24 19:30
FAD03ISTNWDAG | FAD03ISTNWDAB | 9 | FINISH <= START | N | Justification: P, load seats prior to install, 10/11/24, 3563331.; Notes: WDAG->WDAB true 100% of the time over 18 lines. Slack: 2 | 2025-09-24 18:00
FAD01TES57001--A | FAD2AWTCB603R | 8 | FINISH <= START | Y | Justification: P, CTP must complete prior to wash and closure, 6/2/25, 3456276.; Notes: 1--A->603R true 0% of the time over 0 lines. Slack: NA | 2025-09-24 19:11
FAD01TES42001 | FAD01TES21024 | 9 | FINISH <= START | N | Justification: P, CCS needed before testing heating, 3278686, 6/4/25.; Notes: 2001->1024 true 89% of the time over 160 lines. Slack: 2 | 2025-09-24 18:01
FAD2BIECW4323 | FAD2BIECW4321 | 8 | FINISH <= START | N | Justification: P, install wire bundle before verifying routing, 10/3/24, 3563331.; Notes: 4323->4321 true 76% of the time over 147 lines. Slack: 0 | 2025-09-24 19:22
FAD01MHMB125A | FAD01950BD3AA | 10 | FINISH <= START | N | Justification: P, line move to be complete before starting P2 SOW, 8/5/24, 3582167.; Notes: 125A->D3AA true 98% of the time over 160 lines. Slack: 6 | 2025-09-24 20:14
FAD2AICSNL54A | FAD2AICSNL85A | 8 | FINISH <= START | N | Justification: p, install ceilings before tape, 6/24/24, 3582167.; Notes: L54A->L85A true 41% of the time over 12 lines. Slack: 0 | 2025-09-24 19:00
FAD2BBMFN43TR | FAD2BIFCNM1MA | 8 | FINISH <= START | N | Justification: P, Mat on top of floor tape (R Gelzer), 8/22/2024, 3504081.; Notes: 43TR->M1MA true 100% of the time over 11 lines. Slack: 19 | 2025-09-24 19:45
FAD03ISTNHAAF | FAD03ISTNHCDG | 9 | FINISH <= START | N | Justification: P, prepare passenger seats prior to loading them on the plane, 5/23/24, 3563331.; Notes: HAAF->HCDG true 0% of the time over 0 lines. Slack: NA | 2025-09-24 18:23
FAD29ILGNWR3M | FAD03ISTN32YM | 9 | FINISH <= START | N | Justification: P, install EDWs before loading seats, 10-23-2024, 35563331.; Notes: WR3M->32YM true 0% of the time over 0 lines. Slack: NA | 2025-09-24 18:34
FAD2BISTNBSFL | FAD03ISTN2BAG | 9 | FINISH <= START | N | Justification: P, bulbseal is easier to install prior to loading seats, 7/5/24, 3563331.; Notes: BSFL->2BAG true 92% of the time over 13 lines. Slack: 2 | 2025-09-24 18:26
FAD2AWBJB420L | FAD2AWBJB423L | 9 | FINISH <= START | N | Justification: P, Need DJ installed prior to drilling, 5/29/24, 2155637.; Notes: 420L->423L true 41% of the time over 12 lines. Slack: 0 | 2025-09-24 18:14
FAD01WLAB040B | FAD29WLAB017R | 9 | FINISH <= START | N | Justification: Q, Protection should be installed prior to work being performed, 6/1/24, 2155637.; Notes: 040B->017R true 92% of the time over 96 lines. Slack: 1 | 2025-09-24 18:23
FAD29WTSH5R01 | FAD29WTSH5R02 | 8 | FINISH <= START | Y | Justification: P, drag brace area SOW to drag brace install, 3543740, 06/23/2025; Notes: 5R01->5R02 true 100% of the time over 148 lines. Slack: 12 | 2025-09-24 19:01
FAD2ABAJB0210 | FAD01HSJS4100 | 8 | FINISH <= START | Y | Justification: ; Notes: 0210->4100 true 100% of the time over 12 lines. Slack: 3 | 2025-09-24 19:45
FAD29WLSW827L | FAD29WLSW611L | 10 | FINISH <= START | N | Justification: P, connect wires to side body to perm route them, 09/07/2024, 3543740.; Notes: 827L->611L true 94% of the time over 148 lines. Slack: 1 | 2025-09-24 20:28
FAD03BOSS0557 | FAD03BOSS2217 | 9 | FINISH <= START | N | Justification: P, Module attaches to dripshield (R Gelzer), 10/8/2024, 3504081.; Notes: 0557->2217 true 86% of the time over 22 lines. Slack: 1 | 2025-09-24 18:16
FAD20BAJB1128 | FAD20BAJB1364 | 10 | FINISH <= START | Y | Justification: P, finsih drilling before installing fittings, 5/13/25, 3531130.; Notes: 1128->1364 true 94% of the time over 52 lines. Slack: 0 | 2025-09-24 20:11
FAD2BISTNA02M | FAD2BIMTNF2A3 | 10 | FINISH <= START | N | Justification: P, need to install attendant seat before applying FDA seal, 4/30/24, 3563331.; Notes: A02M->F2A3 true 88% of the time over 119 lines. Slack: 0 | 2025-09-24 20:40
FAD2AWBJB7629 | FAD2AWBJB742L | 10 | FINISH <= START | Y | Justification: P, Seal SOW Precedence for 8s, 2/13/25, 3456276.; Notes: 7629->742L true 58% of the time over 12 lines. Slack: 0 | 2025-09-24 20:12
FAD03ISTNWGBB | FAD2BISTN04CM | 8 | FINISH <= START | N | Justification: P, must torque harper fittings prior to installing overlapping seat track covers, 10/14/24, 3563331.; Notes: WGBB->04CM true 0% of the time over 10 lines. Slack: -15 | 2025-09-24 19:22
FAD29BAJB0110 | FAD29BAJB1042 | 9 | FINISH <= START | N | Justification: P, Fasten strap then Fill angles, 10/7/24, 3531130.; Notes: 0110->1042 true 84% of the time over 96 lines. Slack: 0 | 2025-09-24 17:50
FAD2BEBUP670L | FAD2BEBUP680L | 10 | FINISH <= START | N | Justification: E, it is easier to install the aft centerbody before installing the nozzleE, it is easier to install the aft centerbody before installing the nozzle; Notes: FAD2BEBUP670L -> FAD2BEBUP68 | 2025-03-14 05:14
FAD29WWTB063R | FAD29WWTB071R | 10 | FINISH <= START | N | Justification: P, apply aeroseal before painting, 6/2/25, 3715783.; Notes: 063R->071R true 95% of the time over 24 lines. Slack: 0 | 2025-09-24 20:52
FADCEBAJB0002 | FAD2AICSNRTCA | 9 | FINISH <= START | N | Justification: P, complete customer before roller trays cover area, 2/6/25, 3531130.; Notes: 0002->RTCA true 41% of the time over 12 lines. Slack: -1 | 2025-09-24 17:57
FAD2BILGNF1LA | FAD2BIECW0311 | 10 | FINISH <= START | N | Justification: P, Wire routes on fairing (A Hutchinson), 7/2/2024, 3504081.; Notes: F1LA->0311 true 78% of the time over 51 lines. Slack: 1 | 2025-09-24 20:26
FAD2ABAJB0413 | FAD2ABAJB0110 | 8 | FINISH <= START | N | Justification: Q, Check Gaps before fastening strap, 5/14/24, 3531130.; Notes: 0413->0110 true 100% of the time over 3 lines. Slack: 0 | 2025-09-24 19:40
FAD01TES21017 | FAD2BTES21027 | 8 | FINISH <= START | N | Justification: P, Prerequisite Test called out on JITT ZM21712027:0001, 6/12/24, 3278686.; Notes: 1017->1027 true 99% of the time over 135 lines. Slack: 30 | 2025-09-24 19:47
FAD29WBJB7634 | FAD29WBJB7636 | 8 | FINISH <= START | Y | Justification: P, Seal SOW precedence, 9/10/25, 3456276; Notes: 7634->7636 true 75% of the time over 148 lines. Slack: 0 | 2025-09-24 19:51
FAD20BAJB0030 | FAD20BAJB0414 | 9 | FINISH <= START | N | Justification: Q, Check Gaps after drilling full size holes, 5/13/24, 3531130.; Notes: 0030->0414 true 96% of the time over 25 lines. Slack: 0 | 2025-09-24 17:57
FAD2AWFTB232L | FAD2AWMTB550L | 8 | FINISH <= START | N | Justification: 3575876, Panels must be removed before spoiler installs can be done.; Notes: 232L->550L true 100% of the time over 12 lines. Slack: 0 | 2025-09-24 19:54
FAD29WBJB7024 | FAD29WBJB7034--1 | 8 | FINISH <= START | N | Justification: LINK ADDED BASED ON PRIMARY JOB PRECEDENCE 5/30/25. NEEDS BEMS NEEDS BEMS; Notes: 7024->4--1 true 0% of the time over 0 lines. Slack: NA | 2025-09-24 19:29
FAD01HSSW643L | FAD01HSSH200L | 9 | FINISH <= START | N | Justification: P, Part overlap analysis 6/4/2024, 2626909.; Notes: 643L->200L true 99% of the time over 160 lines. Slack: 1 | 2025-09-24 17:44
FAD2BIMTN1C56 | FAD2BICSNC01C | 10 | FINISH <= START | N | Justification: P, Interface attaches to waste water connection (J Weaver), 9/10/2024, 3504081.; Notes: 1C56->C01C true 54% of the time over 24 lines. Slack: 0 | 2025-09-24 20:36
FAD2BIMTN4L04 | FAD2BIMTN4L10 | 10 | FINISH <= START | N | Justification: P, load galley prior to assembling and connecting to the aircraft, 5/11/24, 3563331.; Notes: 4L04->4L10 true 50% of the time over 2 lines. Slack: 0 | 2025-09-24 20:34
FAD2ABASS4111 | FAD2BBFFN813J | 9 | FINISH <= START | N | Justification: P, CRN cables are prefered to be worked before floor panels go in, 7/17/24, 3531130.; Notes: 4111->813J true 100% of the time over 9 lines. Slack: 4 | 2025-09-24 17:49
FAD29VFRB0040 | FAD29VFRB0093 | 10 | FINISH <= START | N | Justification: P, Part overlap analysis 6/4/2024, 2626909.; Notes: 0040->0093 true 100% of the time over 147 lines. Slack: 2 | 2025-09-24 20:19
FAD2BIMTNLR25 | FAD2BIMTNLR29 | 10 | FINISH <= START | N | Justification: P, load lavatory prior to installing sealant, 5/13/24, 3563331.; Notes: LR25->LR29 true 35% of the time over 95 lines. Slack: 0 | 2025-09-24 20:28
FAD2BIMTNLR25 | FAD2BIMTNLR28 | 10 | FINISH <= START | N | Justification: P, lav must be loaded onto the airplane in order to connect components. NEEDS BEMS NEEDS BEMS; Notes: LR25->LR28 true 43% of the time over 128 lines. Slack: 0 | 2025-09-24 20:28